## Tasks
Task ID | Title | Component | Subcomponent | Component Owner | Assignee | Status | Progress % | Estimated Hours | Estimated Cost (USD) | Dependencies | Priority | Project | Created At | Completed At | Comments | Tags
BIG2001 | Payments: Gateway Integration - Implement | Payments | Gateway Integration | Arjun Kumar | Arjun Kumar | Completed | 100 | 40 | 1400 | BIG2055 | Medium | Billing System | 2025-11-02 10:08:00 | 2025-11-12 16:08:00 | Pending security review. | research,critical,performance
BIG2002 | Security: Vulnerability Fixes - Improve | Security | Vulnerability Fixes | Ava Thompson | Ava Thompson | Completed | 100 | 8 | 280 | BIG2014 | Medium | Web Portal | 2025-10-02 12:44:00 | 2025-10-08 16:44:00 | Needs performance tests. | design
BIG2003 | DevOps: Monitoring - Design | DevOps | Monitoring | Sana Roy | Sana Roy | Blocked | 45 | 16 | 400 |  | Low | Analytics Suite | 2025-10-26 11:21:00 |  | Pending security review. | enhancement
BIG2004 | Auth: OAuth - Improve | Auth | OAuth | Sophia Clark | Sophia Clark | Completed | 100 | 24 | 840 |  | Medium | API Services | 2025-09-05 15:56:00 | 2025-09-10 23:56:00 | Requires design sign-off. | minor
BIG2005 | Analytics: Events - Design | Analytics | Events | Lucas Young | James Scott | In Progress | 80 | 40 | 1800 | BIG2002 | Medium | Core Platform | 2025-09-20 12:44:00 |  | Docs required. | bug,security
BIG2006 | Search: Indexing - Fix | Search | Indexing | Ella Johnson | Ella Johnson | Completed | 100 | 24 | 840 | BIG2026 | High | Web Portal | 2025-11-03 12:38:00 | 2025-11-07 16:38:00 | Needs performance tests. | research,refactor
BIG2007 | Database: Schema - Improve | Database | Schema | Harper Adams | Mason Hall | Review | 65 | 4 | 100 |  | High | API Services | 2025-11-13 16:09:00 |  | Owner to update status. | refactor,performance
BIG2008 | API: REST Endpoints - Fix | API | REST Endpoints | Sophia Clark | Sophia Clark | Completed | 100 | 4 | 180 |  | Medium | Mobile App | 2025-10-11 15:47:00 | 2025-10-13 16:47:00 | QA passed. | ux,design
BIG2009 | UI: Forms - Fix | UI | Forms | Mia Lewis | Mia Lewis | Open | 88 | 16 | 560 | BIG2062 | Medium | Analytics Suite | 2025-10-22 16:17:00 |  | Needs performance tests. | performance,enhancement,bug
BIG2010 | Search: Filters - Design | Search | Filters | Noah Davis | Noah Davis | Open | 87 | 4 | 140 |  | Medium | Billing System | 2025-10-19 14:39:00 |  | Blocked by API team. | bug
BIG2011 | Notifications: Push - Test | Notifications | Push | Ethan Walker | Rohan Iyer | Completed | 100 | 24 | 1080 |  | Medium | API Services | 2025-11-13 12:42:00 | 2025-11-19 20:42:00 | Owner to update status. | security
BIG2012 | Auth: Login - Test | Auth | Login | Mia Lewis | Mia Lewis | Blocked | 9 | 8 | 360 | BIG2097 | Medium | Web Portal | 2025-10-31 16:55:00 |  | Docs required. | security
BIG2013 | Analytics: Dashboards - Implement | Analytics | Dashboards | Mason Hall | Mason Hall | In Progress | 57 | 16 | 720 |  | Critical | API Services | 2025-11-13 16:05:00 |  | Requires design sign-off. | performance,security
BIG2014 | Auth: Login - Design | Auth | Login | Sophia Clark | Sana Roy | Completed | 100 | 12 | 540 |  | High | Web Portal | 2025-11-05 17:13:00 | 2025-11-13 22:13:00 | Merge conflict to resolve. | refactor,bug,security
BIG2015 | Database: Schema - Fix | Database | Schema | Sophia Clark | Sophia Clark | Completed | 100 | 4 | 140 | BIG2022 | Low | API Services | 2025-10-08 17:33:00 | 2025-10-14 18:33:00 | Pending security review. | research,ux,bug
BIG2016 | Database: Backups - Implement | Database | Backups | Rohan Iyer | Liam Brown | Open | 86 | 40 | 1000 |  | High | Billing System | 2025-10-24 09:59:00 |  | Merge conflict to resolve. | refactor
BIG2017 | Security: AuthZ - Improve | Security | AuthZ | Priya Singh | Priya Singh | Review | 22 | 24 | 840 |  | High | Mobile App | 2025-11-14 16:59:00 |  | Blocked by API team. | ux,critical,minor
BIG2018 | Search: Ranking - Implement | Search | Ranking | Priya Singh | James Scott | In Progress | 17 | 8 | 360 | BIG2053 | High | Admin Dashboard | 2025-10-14 13:28:00 |  | QA passed. | research,ux,security
BIG2019 | Payments: Refunds - Fix | Payments | Refunds | Arjun Kumar | Lucas Young | Review | 88 | 24 | 840 | BIG2082 | High | Analytics Suite | 2025-11-23 11:32:00 |  | QA passed. | minor,security,design
BIG2020 | Auth: Login - Improve | Auth | Login | Ethan Walker | Ethan Walker | Open | 20 | 12 | 300 | BIG2037 | Low | Core Platform | 2025-11-25 09:12:00 |  | Docs required. | performance,critical,refactor
BIG2021 | Search: Ranking - Test | Search | Ranking | Liam Brown | Priya Singh | Completed | 100 | 40 | 1000 |  | High | Billing System | 2025-11-22 17:24:00 | 2025-11-27 01:24:00 | Pending security review. | performance,ux,design
BIG2022 | Search: Filters - Implement | Search | Filters | Sophia Clark | Sophia Clark | Completed | 100 | 16 | 560 |  | Low | Mobile App | 2025-11-09 12:49:00 | 2025-11-13 16:49:00 | Blocked by API team. | design,security
BIG2023 | API: GraphQL - Design | API | GraphQL | Arjun Kumar | James Scott | Open | 41 | 8 | 360 |  | High | API Services | 2025-10-30 11:02:00 |  | Docs required. | critical,bug,ux
BIG2024 | Database: Migrations - Design | Database | Migrations | Mason Hall | Mason Hall | Completed | 100 | 4 | 140 |  | High | API Services | 2025-09-21 15:34:00 | 2025-09-30 21:34:00 | QA passed. | research,security
BIG2025 | Security: AuthZ - Improve | Security | AuthZ | Ella Johnson | Ella Johnson | Completed | 100 | 4 | 180 | BIG2088 | Medium | Analytics Suite | 2025-10-28 12:57:00 | 2025-11-07 15:57:00 | Blocked by API team. | design,performance,critical
BIG2026 | Security: Encryption - Refactor | Security | Encryption | Elijah Green | Liam Roberts | In Progress | 10 | 24 | 600 |  | Critical | Analytics Suite | 2025-11-23 12:20:00 |  | Requires design sign-off. | research,minor,bug
BIG2027 | Security: AuthZ - Test | Security | AuthZ | Arjun Kumar | Olivia Miller | Completed | 100 | 4 | 140 |  | Low | Analytics Suite | 2025-09-10 11:01:00 | 2025-09-18 16:01:00 | Docs required. | design
BIG2028 | Analytics: Dashboards - Test | Analytics | Dashboards | Mason Hall | Ethan Walker | In Progress | 68 | 4 | 140 |  | High | Admin Dashboard | 2025-09-03 15:43:00 |  | Requires design sign-off. | security,bug
BIG2029 | Payments: Refunds - Improve | Payments | Refunds | Lucas Young | Harper Adams | Completed | 100 | 8 | 360 |  | Low | Billing System | 2025-10-27 15:25:00 | 2025-10-28 22:25:00 | Docs required. | critical,performance
BIG2030 | Security: Vulnerability Fixes - Improve | Security | Vulnerability Fixes | Liam Roberts | Liam Roberts | Open | 10 | 24 | 600 |  | High | API Services | 2025-11-16 15:34:00 |  | QA passed. | security,enhancement,ux
BIG2031 | Database: Indexes - Implement | Database | Indexes | Ella Johnson | Ella Johnson | Open | 59 | 24 | 840 |  | Low | Core Platform | 2025-11-12 09:54:00 |  | Docs required. | ux,refactor,critical
BIG2032 | API: GraphQL - Improve | API | GraphQL | Olivia Miller | Harper Adams | Completed | 100 | 24 | 840 | BIG2085 | Medium | Mobile App | 2025-09-25 14:31:00 | 2025-10-03 19:31:00 | QA passed. | performance
BIG2033 | Database: Migrations - Test | Database | Migrations | Ella Johnson | Olivia Miller | In Progress | 42 | 40 | 1000 | BIG2062 | Medium | Analytics Suite | 2025-10-17 11:43:00 |  | Docs required. | ux
BIG2034 | Payments: Gateway Integration - Design | Payments | Gateway Integration | Elijah Green | Elijah Green | In Progress | 2 | 4 | 140 |  | High | Admin Dashboard | 2025-11-20 10:46:00 |  | Pending security review. | security
BIG2035 | Security: AuthZ - Refactor | Security | AuthZ | Sana Roy | Lucas Young | In Progress | 64 | 16 | 560 |  | Medium | Admin Dashboard | 2025-09-29 13:08:00 |  | Requires design sign-off. | enhancement,security,ux
BIG2036 | API: GraphQL - Design | API | GraphQL | Rohan Iyer | Arjun Kumar | Completed | 100 | 16 | 560 |  | Low | Mobile App | 2025-09-19 16:22:00 | 2025-09-20 19:22:00 | Requires design sign-off. | minor,refactor
BIG2037 | Auth: Login - Test | Auth | Login | Mason Hall | Liam Brown | Open | 33 | 40 | 1800 |  | Medium | Billing System | 2025-11-06 13:53:00 |  | QA passed. | design,minor,research
BIG2038 | Analytics: Dashboards - Fix | Analytics | Dashboards | Zara Patel | Zara Patel | Completed | 100 | 8 | 360 |  | Medium | Web Portal | 2025-11-17 09:32:00 | 2025-11-20 16:32:00 | Owner to update status. | critical
BIG2039 | UI: Dashboard - Refactor | UI | Dashboard | Liam Brown | Liam Brown | Completed | 100 | 40 | 1000 |  | Low | Mobile App | 2025-11-01 16:30:00 | 2025-11-05 18:30:00 | Needs performance tests. | performance,enhancement,ux
BIG2040 | Payments: Gateway Integration - Design | Payments | Gateway Integration | Zara Patel | Ethan Walker | Blocked | 93 | 40 | 1400 | BIG2085 | High | Mobile App | 2025-11-12 09:56:00 |  | Merge conflict to resolve. | enhancement,research
BIG2041 | Search: Indexing - Design | Search | Indexing | Mia Lewis | Mia Lewis | Completed | 100 | 24 | 1080 |  | Low | Billing System | 2025-11-05 13:10:00 | 2025-11-11 20:10:00 | Needs performance tests. | security
BIG2042 | Analytics: Events - Design | Analytics | Events | Priya Singh | Ella Johnson | Open | 64 | 24 | 1080 |  | Low | API Services | 2025-11-18 09:56:00 |  | Needs performance tests. | minor
BIG2043 | Analytics: Dashboards - Improve | Analytics | Dashboards | Mason Hall | Rohan Iyer | In Progress | 94 | 24 | 840 |  | Medium | Web Portal | 2025-11-01 15:22:00 |  | Merge conflict to resolve. | ux,security
BIG2044 | Payments: Gateway Integration - Improve | Payments | Gateway Integration | Arjun Kumar | Ava Thompson | Blocked | 83 | 16 | 560 | BIG2027 | Medium | Core Platform | 2025-09-16 17:00:00 |  | Needs performance tests. | design,security
BIG2045 | Search: Filters - Design | Search | Filters | James Scott | James Scott | Review | 71 | 24 | 1080 |  | Medium | Admin Dashboard | 2025-10-21 12:26:00 |  | Merge conflict to resolve. | ux,critical
BIG2046 | Analytics: ETL - Implement | Analytics | ETL | Lucas Young | Ella Johnson | Completed | 100 | 16 | 400 |  | Low | API Services | 2025-10-28 11:06:00 | 2025-11-01 19:06:00 | Requires design sign-off. | ux,minor
BIG2047 | UI: Forms - Implement | UI | Forms | Mia Lewis | Sophia Clark | Open | 78 | 16 | 400 | BIG2084 | High | Admin Dashboard | 2025-09-05 15:59:00 |  | Requires design sign-off. | refactor,ux,performance
BIG2048 | Security: Encryption - Implement | Security | Encryption | Liam Roberts | Liam Roberts | Completed | 100 | 40 | 1800 | BIG2005 | Low | Core Platform | 2025-11-05 17:44:00 | 2025-11-09 19:44:00 | Needs performance tests. | minor,critical
BIG2049 | Analytics: Dashboards - Design | Analytics | Dashboards | Elijah Green | Elijah Green | Blocked | 70 | 4 | 140 | BIG2037 | Medium | Analytics Suite | 2025-11-30 10:58:00 |  | Docs required. | refactor
BIG2050 | Search: Indexing - Fix | Search | Indexing | Ethan Walker | Mia Lewis | In Progress | 37 | 24 | 840 |  | High | Web Portal | 2025-09-14 17:04:00 |  | Docs required. | refactor,research,critical
BIG2051 | DevOps: Monitoring - Improve | DevOps | Monitoring | Ava Thompson | Zara Patel | Open | 86 | 8 | 200 |  | High | Billing System | 2025-09-09 15:40:00 |  | QA passed. | design,research,ux
BIG2052 | Analytics: ETL - Test | Analytics | ETL | Elijah Green | Liam Brown | Open | 27 | 12 | 420 | BIG2074 | Low | API Services | 2025-09-23 16:20:00 |  | Owner to update status. | research
BIG2053 | Database: Migrations - Implement | Database | Migrations | Sophia Clark | Amelia Baker | Completed | 100 | 4 | 140 | BIG2087 | Medium | Analytics Suite | 2025-10-16 11:49:00 | 2025-10-18 12:49:00 | Requires design sign-off. | critical,refactor,design
BIG2054 | API: Rate Limiting - Refactor | API | Rate Limiting | Ella Johnson | Amelia Baker | Completed | 100 | 24 | 1080 | BIG2005 | Medium | API Services | 2025-09-17 09:33:00 | 2025-09-24 16:33:00 | Needs performance tests. | security,refactor,critical
BIG2055 | Auth: Login - Test | Auth | Login | Elijah Green | Elijah Green | In Progress | 33 | 24 | 840 | BIG2024 | Low | Billing System | 2025-09-13 14:23:00 |  | QA passed. | minor,research
BIG2056 | Notifications: Email - Refactor | Notifications | Email | Elijah Green | James Scott | In Progress | 29 | 40 | 1400 | BIG2013 | High | Admin Dashboard | 2025-11-13 11:36:00 |  | Pending security review. | enhancement
BIG2057 | Auth: OAuth - Refactor | Auth | OAuth | Zara Patel | Zara Patel | Open | 40 | 40 | 1400 | BIG2063 | Low | Analytics Suite | 2025-11-20 17:34:00 |  | Requires design sign-off. | enhancement,performance,research
BIG2058 | DevOps: Monitoring - Improve | DevOps | Monitoring | Priya Singh | Noah Davis | Completed | 100 | 12 | 420 |  | Medium | Web Portal | 2025-10-04 14:23:00 | 2025-10-13 22:23:00 | Owner to update status. | design
BIG2059 | Notifications: SMS - Design | Notifications | SMS | Sana Roy | Zara Patel | Completed | 100 | 16 | 400 |  | High | API Services | 2025-10-28 10:24:00 | 2025-11-07 14:24:00 | QA passed. | minor,bug,security
BIG2060 | Notifications: Push - Fix | Notifications | Push | Mia Lewis | Liam Brown | Completed | 100 | 16 | 720 | BIG2100 | High | Admin Dashboard | 2025-11-30 13:38:00 | 2025-12-07 17:38:00 | Merge conflict to resolve. | enhancement
BIG2061 | Database: Indexes - Test | Database | Indexes | Mason Hall | Mason Hall | In Progress | 60 | 4 | 140 |  | Low | Billing System | 2025-10-21 10:06:00 |  | Blocked by API team. | enhancement,bug,minor
BIG2062 | Database: Migrations - Test | Database | Migrations | Priya Singh | Harper Adams | In Progress | 3 | 8 | 200 | BIG2005 | High | Web Portal | 2025-09-17 11:33:00 |  | Merge conflict to resolve. | security,refactor
BIG2063 | Security: Vulnerability Fixes - Design | Security | Vulnerability Fixes | Noah Davis | Sana Roy | In Progress | 81 | 40 | 1400 | BIG2069 | High | Billing System | 2025-11-21 15:33:00 |  | Owner to update status. | critical,minor
BIG2064 | API: Rate Limiting - Improve | API | Rate Limiting | Ava Thompson | Ava Thompson | Blocked | 68 | 16 | 400 | BIG2002 | High | Billing System | 2025-09-18 14:18:00 |  | Docs required. | design,research
BIG2065 | Security: Encryption - Implement | Security | Encryption | Sana Roy | Olivia Miller | Completed | 100 | 16 | 560 | BIG2029 | Low | API Services | 2025-10-26 15:15:00 | 2025-10-29 21:15:00 | Owner to update status. | design,ux,security
BIG2066 | Database: Schema - Implement | Database | Schema | Lucas Young | Lucas Young | In Progress | 34 | 16 | 560 | BIG2090 | Low | Core Platform | 2025-11-21 16:39:00 |  | Needs performance tests. | performance,enhancement,bug
BIG2067 | Payments: Gateway Integration - Test | Payments | Gateway Integration | Noah Davis | Noah Davis | Completed | 100 | 8 | 200 | BIG2044 | Medium | Analytics Suite | 2025-09-30 10:09:00 | 2025-10-01 17:09:00 | Merge conflict to resolve. | performance,critical,bug
BIG2068 | Auth: Session - Refactor | Auth | Session | Mason Hall | Mason Hall | Blocked | 48 | 12 | 300 |  | Critical | API Services | 2025-09-24 12:57:00 |  | Owner to update status. | research,performance
BIG2069 | DevOps: Monitoring - Improve | DevOps | Monitoring | Rohan Iyer | Rohan Iyer | Completed | 100 | 8 | 200 |  | High | Admin Dashboard | 2025-09-27 16:24:00 | 2025-10-02 21:24:00 | Blocked by API team. | design,research,critical
BIG2070 | Database: Schema - Implement | Database | Schema | Lucas Young | Olivia Miller | In Progress | 50 | 4 | 100 |  | Critical | Admin Dashboard | 2025-09-22 13:37:00 |  | Merge conflict to resolve. | bug,research
BIG2071 | DevOps: CI/CD - Test | DevOps | CI/CD | Sophia Clark | Sana Roy | In Progress | 82 | 12 | 540 |  | Low | Mobile App | 2025-11-20 09:03:00 |  | QA passed. | research,performance
BIG2072 | Analytics: Dashboards - Test | Analytics | Dashboards | Lucas Young | Lucas Young | In Progress | 71 | 16 | 400 | BIG2038 | Low | Mobile App | 2025-09-06 16:45:00 |  | QA passed. | design,security
BIG2073 | UI: Dashboard - Refactor | UI | Dashboard | Amelia Baker | Harper Adams | Completed | 100 | 16 | 560 |  | High | Admin Dashboard | 2025-11-09 14:29:00 | 2025-11-10 22:29:00 | QA passed. | bug,security
BIG2074 | Database: Backups - Design | Database | Backups | Elijah Green | Lucas Young | Completed | 100 | 4 | 100 |  | Low | Mobile App | 2025-10-12 15:41:00 | 2025-10-18 16:41:00 | Needs performance tests. | refactor
BIG2075 | UI: Landing - Design | UI | Landing | Mason Hall | Ethan Walker | Completed | 100 | 24 | 1080 |  | Low | Mobile App | 2025-11-07 13:03:00 | 2025-11-13 16:03:00 | Merge conflict to resolve. | performance,critical
BIG2076 | Analytics: Dashboards - Test | Analytics | Dashboards | Liam Roberts | Liam Roberts | Completed | 100 | 4 | 180 |  | Low | Mobile App | 2025-10-05 17:02:00 | 2025-10-07 21:02:00 | Pending security review. | research,enhancement,minor
BIG2077 | UI: Forms - Test | UI | Forms | Liam Brown | Noah Davis | Completed | 100 | 16 | 720 | BIG2065 | Medium | Admin Dashboard | 2025-10-25 10:10:00 | 2025-10-28 18:10:00 | Merge conflict to resolve. | critical,ux,minor
BIG2078 | Analytics: ETL - Fix | Analytics | ETL | Sana Roy | Sana Roy | In Progress | 95 | 24 | 1080 | BIG2033 | Critical | Billing System | 2025-11-09 12:24:00 |  | Pending security review. | design
BIG2079 | Auth: OAuth - Fix | Auth | OAuth | Ava Thompson | Ava Thompson | In Progress | 2 | 12 | 300 | BIG2099 | High | Admin Dashboard | 2025-09-29 12:54:00 |  | Needs performance tests. | critical,enhancement
BIG2080 | Payments: Billing - Design | Payments | Billing | Amelia Baker | Amelia Baker | In Progress | 72 | 16 | 400 |  | High | Analytics Suite | 2025-10-09 10:36:00 |  | Merge conflict to resolve. | ux,bug,design
BIG2081 | Search: Filters - Improve | Search | Filters | Ethan Walker | Liam Roberts | Review | 53 | 16 | 720 |  | High | Analytics Suite | 2025-10-13 14:56:00 |  | Requires design sign-off. | design
BIG2082 | Auth: Session - Design | Auth | Session | Arjun Kumar | Arjun Kumar | Open | 86 | 4 | 100 | BIG2094 | Critical | Analytics Suite | 2025-11-04 12:09:00 |  | Blocked by API team. | minor,enhancement
BIG2083 | Notifications: Push - Refactor | Notifications | Push | Arjun Kumar | Arjun Kumar | Completed | 100 | 24 | 1080 |  | High | Billing System | 2025-11-10 15:16:00 | 2025-11-12 21:16:00 | Owner to update status. | security
BIG2084 | Security: Vulnerability Fixes - Implement | Security | Vulnerability Fixes | Mason Hall | Mason Hall | In Progress | 11 | 24 | 840 | BIG2015 | Medium | Web Portal | 2025-10-26 14:43:00 |  | Owner to update status. | performance,design,enhancement
BIG2085 | Search: Filters - Design | Search | Filters | Lucas Young | Lucas Young | In Progress | 19 | 12 | 540 |  | Low | Core Platform | 2025-09-30 12:43:00 |  | Owner to update status. | performance,critical
BIG2086 | UI: Forms - Refactor | UI | Forms | Ava Thompson | Zara Patel | Open | 69 | 8 | 200 | BIG2067 | Medium | Admin Dashboard | 2025-09-27 17:13:00 |  | Needs performance tests. | ux,security
BIG2087 | Payments: Gateway Integration - Improve | Payments | Gateway Integration | Ava Thompson | Harper Adams | In Progress | 83 | 16 | 560 |  | Medium | Web Portal | 2025-11-29 13:03:00 |  | QA passed. | minor,research
BIG2088 | Security: AuthZ - Improve | Security | AuthZ | Liam Brown | Liam Brown | In Progress | 25 | 8 | 280 | BIG2065 | Medium | API Services | 2025-11-16 17:05:00 |  | Requires design sign-off. | design,critical,refactor
BIG2089 | API: REST Endpoints - Fix | API | REST Endpoints | James Scott | Sophia Clark | In Progress | 7 | 12 | 420 | BIG2081 | High | Analytics Suite | 2025-10-09 12:32:00 |  | Requires design sign-off. | enhancement
BIG2090 | Analytics: ETL - Implement | Analytics | ETL | Arjun Kumar | Mason Hall | Completed | 100 | 16 | 720 | BIG2040 | Medium | Mobile App | 2025-11-06 12:26:00 | 2025-11-10 14:26:00 | Owner to update status. | research,enhancement,design
BIG2091 | Security: Vulnerability Fixes - Refactor | Security | Vulnerability Fixes | Liam Brown | Lucas Young | Completed | 100 | 24 | 840 |  | Low | Analytics Suite | 2025-11-12 11:20:00 | 2025-11-14 19:20:00 | Needs performance tests. | minor,design
BIG2092 | Payments: Gateway Integration - Implement | Payments | Gateway Integration | Ella Johnson | Ella Johnson | Open | 78 | 24 | 1080 |  | Low | Core Platform | 2025-09-04 13:38:00 |  | QA passed. | enhancement,security
BIG2093 | DevOps: Monitoring - Test | DevOps | Monitoring | Olivia Miller | Sophia Clark | Open | 20 | 8 | 200 |  | Low | Analytics Suite | 2025-10-20 16:30:00 |  | Requires design sign-off. | research
BIG2094 | UI: Dashboard - Refactor | UI | Dashboard | Ethan Walker | Sana Roy | In Progress | 54 | 8 | 360 |  | Medium | Analytics Suite | 2025-10-12 16:56:00 |  | Pending security review. | ux,security,performance
BIG2095 | UI: Components - Refactor | UI | Components | Harper Adams | Liam Roberts | Completed | 100 | 24 | 840 |  | Low | Billing System | 2025-10-02 17:34:00 | 2025-10-09 17:34:00 | Pending security review. | enhancement,minor
BIG2096 | Search: Indexing - Test | Search | Indexing | Rohan Iyer | Rohan Iyer | Review | 64 | 40 | 1000 |  | High | API Services | 2025-10-30 16:05:00 |  | Needs performance tests. | refactor,performance
BIG2097 | DevOps: Monitoring - Test | DevOps | Monitoring | Rohan Iyer | Elijah Green | Completed | 100 | 4 | 100 | BIG2015 | Medium | Core Platform | 2025-09-12 13:20:00 | 2025-09-15 14:20:00 | Pending security review. | enhancement,minor,security
BIG2098 | API: Rate Limiting - Design | API | Rate Limiting | Lucas Young | Lucas Young | Open | 6 | 40 | 1000 | BIG2054 | Medium | Analytics Suite | 2025-09-19 11:49:00 |  | Merge conflict to resolve. | bug
BIG2099 | Database: Schema - Design | Database | Schema | Noah Davis | James Scott | Open | 77 | 4 | 180 |  | Low | API Services | 2025-11-03 16:34:00 |  | Merge conflict to resolve. | ux
BIG2100 | Auth: OAuth - Design | Auth | OAuth | Sana Roy | James Scott | Completed | 100 | 4 | 100 | BIG2084 | Low | Analytics Suite | 2025-11-11 12:03:00 | 2025-11-14 14:03:00 | Requires design sign-off. | critical,bug

## Component_Summary
Component | Task Count
Security | 13
Analytics | 13
Database | 13
Auth | 11
Search | 11
Payments | 10
UI | 9
API | 8
DevOps | 7
Notifications | 5